## Sheet1
BSL PROJECT PROGRESS TRACKER — Data Entry Sheet
# | Project | Date | Component | Budgeted % | Actual % | Notes
1 | LDC | 2026-04-01 | Boundary Wall | 10 | 50 | Initial mobilisation
2 | LDC | 2026-04-07 | Boundary Wall | 20 | 90
3 | LDC | 2026-04-14 | Boundary Wall | 30 | 95
4 | LDC | 2026-04-21 | Boundary Wall | 42 | 95 | Labour shortage
5 | LDC | 2026-04-28 | Boundary Wall | 55 | 95
6 | LDC | 2026-05-05 | Boundary Wall | 68 | 95
7 | LDC | 2026-05-12 | Boundary Wall | 80 | 95
8 | LDC | 2026-05-19 | Boundary Wall | 90 | 95
9 | LDC | 2026-05-26 | Boundary Wall | 100 | 100 | Snagging remains
10 | LDC | 2026-04-01 | Drainage | 15 | 18 | Ahead — good conditions
11 | LDC | 2026-04-07 | Drainage | 28 | 30
12 | LDC | 2026-04-14 | Drainage | 40 | 44
13 | LDC | 2026-04-21 | Drainage | 52 | 55
14 | LDC | 2026-04-28 | Drainage | 63 | 65
15 | LDC | 2026-05-05 | Drainage | 74 | 74
16 | LDC | 2026-05-12 | Drainage | 84 | 80 | Rain delay
17 | LDC | 2026-05-19 | Drainage | 92 | 87
18 | LDC | 2026-05-26 | Drainage | 100 | 96
19 | LDC | 2026-04-01 | Retrofitting | 5 | 3
20 | LDC | 2026-04-07 | Retrofitting | 12 | 8 | Material delayed
21 | LDC | 2026-04-14 | Retrofitting | 22 | 15
22 | LDC | 2026-04-21 | Retrofitting | 35 | 24 | Design revision
23 | LDC | 2026-04-28 | Retrofitting | 48 | 36
24 | LDC | 2026-05-05 | Retrofitting | 62 | 52
25 | LDC | 2026-05-12 | Retrofitting | 74 | 65
26 | LDC | 2026-05-19 | Retrofitting | 86 | 78
27 | LDC | 2026-05-26 | Retrofitting | 95 | 88
28 | LDC | 2026-04-01 | Road Works | 0 | 0
29 | LDC | 2026-04-07 | Road Works | 5 | 7
30 | LDC | 2026-04-14 | Road Works | 14 | 16
31 | LDC | 2026-04-21 | Road Works | 28 | 30
32 | LDC | 2026-04-28 | Road Works | 44 | 46
33 | LDC | 2026-05-05 | Road Works | 58 | 58
34 | LDC | 2026-05-12 | Road Works | 70 | 66
35 | LDC | 2026-05-19 | Road Works | 82 | 76
36 | LDC | 2026-05-26 | Road Works | 92 | 86
37 | LDC | 2026-04-01 | Structural Repair | 20 | 22
38 | LDC | 2026-04-07 | Structural Repair | 34 | 38
39 | LDC | 2026-04-14 | Structural Repair | 48 | 50
40 | LDC | 2026-04-21 | Structural Repair | 60 | 62
41 | LDC | 2026-04-28 | Structural Repair | 70 | 71
42 | LDC | 2026-05-05 | Structural Repair | 80 | 80
43 | LDC | 2026-05-12 | Structural Repair | 88 | 85
44 | LDC | 2026-05-19 | Structural Repair | 94 | 90
45 | LDC | 2026-05-26 | Structural Repair | 100 | 96
46 | Site B | 2026-04-07 | Foundation | 25 | 22
47 | Site B | 2026-04-14 | Foundation | 50 | 47
48 | Site B | 2026-04-21 | Foundation | 75 | 73
49 | Site B | 2026-04-28 | Foundation | 100 | 95
50 | Site B | 2026-04-07 | Superstructure | 10 | 8
51 | Site B | 2026-04-14 | Superstructure | 30 | 26
52 | Site B | 2026-04-21 | Superstructure | 55 | 50
53 | Site B | 2026-04-28 | Superstructure | 80 | 72
ADD NEW ROWS BELOW THIS LINE ↓ ¦ Required columns: Project, Date (YYYY-MM-DD), Component, Budgeted %, Actual %
YYYY-MM-DD
YYYY-MM-DD
YYYY-MM-DD
YYYY-MM-DD
YYYY-MM-DD