## Project Data
BSL PROJECT PROGRESS TRACKER — Data Entry Sheet
# | Project | Date | Component | Budgeted % | Actual % | Notes
1 | LDC | 2026-04-01 | XYZ | 50 | 75 | Initial mobilisation
2 | LDC | 2026-04-07 | XYZ | 100 | 100
3 | LDC | 2026-04-14 | Boundary Wall | 40 | 10
4 | LDC | 2026-04-21 | Boundary Wall | 42 | 10 | Labour shortage
5 | LDC | 2026-04-28 | Boundary Wall | 55 | 10
6 | LDC | 2026-05-05 | Boundary Wall | 68 | 10
7 | LDC | 2026-05-12 | Boundary Wall | 80 | 95
8 | LDC | 2026-05-19 | Boundary Wall | 90 | 100
9 | LDC | 2026-05-26 | abcd | 100 | 100 | Snagging remains
10 | LDC | 2026-04-01 | Drainage | 15 | 18 | Ahead — good conditions
11 | LDC | 2026-04-07 | XYZ | 20 | 30
12 | LDC | 2026-04-14 | XYZ | 40 | 44
13 | LDC | 2026-04-21 | Drainage | 52 | 55
14 | LDC | 2026-04-28 | XYZ | 63 | 65
15 | LDC | 2026-05-05 | Drainage | 74 | 74
16 | LDC | 2026-05-12 | Drainage | 84 | 80 | Rain delay
17 | LDC | 2026-05-19 | Drainage | 92 | 87
18 | LDC | 2026-05-26 | Drainage | 100 | 96
19 | LDC | 2026-04-01 | Retrofitting | 5 | 3
20 | LDC | 2026-04-07 | Retrofitting | 12 | 8 | Material delayed
21 | LDC | 2026-04-14 | Retrofitting | 22 | 15
22 | LDC | 2026-04-21 | XYZ | 35 | 24 | Design revision
23 | LDC | 2026-04-28 | Retrofitting | 48 | 36
24 | LDC | 2026-05-05 | Retrofitting | 62 | 52
25 | LDC | 2026-05-12 | Retrofitting | 74 | 65
26 | LDC | 2026-05-19 | Retrofitting | 86 | 78
27 | LDC | 2026-05-26 | Retrofitting | 95 | 88
28 | LDC | 2026-04-01 | Road Works | 0 | 0
29 | LDC | 2026-04-07 | Road Works | 5 | 7
30 | LDC | 2026-04-14 | Road Works | 14 | 16
31 | LDC | 2026-04-21 | Road Works | 28 | 30
32 | LDC | 2026-04-28 | Road Works | 44 | 46
33 | LDC | 2026-05-05 | Road Works | 58 | 58
34 | LDC | 2026-05-12 | Road Works | 70 | 66
35 | LDC | 2026-05-19 | Road Works | 82 | 76
36 | LDC | 2026-05-26 | Road Works | 92 | 86
37 | LDC | 2026-04-01 | Structural Repair | 20 | 22
38 | LDC | 2026-04-07 | Structural Repair | 34 | 38
39 | LDC | 2026-04-14 | Structural Repair | 48 | 50
40 | LDC | 2026-04-21 | Structural Repair | 60 | 62
41 | LDC | 2026-04-28 | Structural Repair | 70 | 71
42 | LDC | 2026-05-05 | Structural Repair | 80 | 80
43 | LDC | 2026-05-12 | Structural Repair | 88 | 85
44 | LDC | 2026-05-19 | Structural Repair | 94 | 90
45 | LDC | 2026-05-26 | Structural Repair | 100 | 96
46 | Site B | 2026-04-07 | Foundation | 25 | 22
47 | Site B | 2026-04-14 | Foundation | 50 | 47
48 | Site B | 2026-04-21 | Foundation | 75 | 73
49 | Site B | 2026-04-28 | Foundation | 100 | 95
50 | Site B | 2026-04-07 | Superstructure | 10 | 8
51 | Site B | 2026-04-14 | Superstructure | 30 | 26
52 | Site B | 2026-04-21 | Superstructure | 55 | 50
53 | Site B | 2026-04-28 | Superstructure | 80 | 72
54 | Site c | 2026-04-28 | Foundation | 50 | 25
55 | Site c | 2026-05-28 | Foundation | 75 | 60
56 | Site c | 2026-06-28 | Foundation | 100 | 100
57 | Site c | 2026-07-28 | Material testing | 50 | 55
58 | Site c | 2026-08-28 | Material testing | 60 | 60
59 | Site c | 2026-09-28 | Material testing | 100 | 100

## How To Use
HOW TO USE THIS FILE
STEP-BY-STEP GUIDE
Step 1 | Go to the 'Project Data' sheet (this workbook).
Step 2 | Find the blue section at the bottom: 'ADD NEW ROWS BELOW THIS LINE'.
Step 3 | Add one row per component per date. Fill: Project, Date, Component, Budgeted %, Actual %.
Step 4 | Save this file (Ctrl+S).
Step 5 | Open BSL_Dashboard_v2.html in your browser.
Step 6 | Drag & drop this Excel file onto the upload area at the top of the dashboard.
Step 7 | All charts update instantly. No internet required.
COLUMN RULES — READ CAREFULLY
Project | Name of the project. e.g. LDC or Site B. Must be spelled exactly the same every time.
Date | Format: YYYY-MM-DD only. Example: 2026-05-07. Do NOT use 07/05/2026 or May 7.
Component | Work item name. e.g. Boundary Wall. Must match exactly across dates (case-sensitive).
Budgeted % | The planned completion % for this item on this date. Number only — enter 60, not 60%.
Actual % | Real completion % achieved on site. Number only. Red = behind, Green = ahead.
Notes | Optional. Write any site remarks, delays, or observations.
RULES TO AVOID ERRORS
No duplicates | Each Project + Date + Component combination must appear only once.
Date format | Always YYYY-MM-DD. The dashboard reads dates in this format only.
Numbers only | Budgeted % and Actual % must be plain numbers (0 to 100). No % sign.
Exact names | 'Boundary Wall' and 'boundary wall' are two different components to the dashboard.
Sheet name | Do NOT rename the 'Project Data' sheet — the dashboard looks for this exact name.
ADDING A NEW COMPONENT
Step 1 | Just start adding rows with the new component name in the Project Data sheet.
Step 2 | The dashboard will pick it up automatically — no configuration needed.
COLOR MEANING IN PROJECT DATA SHEET
Blue (Budgeted %) | Planned / scheduled completion for that date.
Green (Actual %) | Actual is AHEAD of budgeted — good progress.
Red (Actual %) | Actual is BEHIND budgeted — needs attention.
Orange (Actual %) | Actual equals budgeted — exactly on track.