## Project Data
Project | Date | Component | Budgeted % | Actual % | Notes
LDC | 2026-04-01 | Boundary Wall | 10 | 8 | Initial mobilisation
LDC | 2026-04-07 | Boundary Wall | 20 | 16
LDC | 2026-04-14 | Boundary Wall | 30 | 26
LDC | 2026-04-21 | Boundary Wall | 42 | 35 | Labour shortage
LDC | 2026-04-28 | Boundary Wall | 55 | 48
LDC | 2026-05-05 | Boundary Wall | 68 | 60
LDC | 2026-05-12 | Boundary Wall | 80 | 72
LDC | 2026-05-19 | Boundary Wall | 90 | 84
LDC | 2026-05-26 | Boundary Wall | 100 | 93 | Snagging remains
LDC | 2026-04-01 | Drainage | 15 | 18 | Ahead — good conditions
LDC | 2026-04-07 | Drainage | 28 | 30
LDC | 2026-04-14 | Drainage | 40 | 44
LDC | 2026-04-21 | Drainage | 52 | 55
LDC | 2026-04-28 | Drainage | 63 | 65
LDC | 2026-05-05 | Drainage | 74 | 74
LDC | 2026-05-12 | Drainage | 84 | 80 | Rain delay
LDC | 2026-05-19 | Drainage | 92 | 87
LDC | 2026-05-26 | Drainage | 100 | 96
LDC | 2026-04-01 | Retrofitting | 5 | 3
LDC | 2026-04-07 | Retrofitting | 12 | 8 | Material delayed
LDC | 2026-04-14 | Retrofitting | 22 | 15
LDC | 2026-04-21 | Retrofitting | 35 | 24 | Design revision
LDC | 2026-04-28 | Retrofitting | 48 | 36
LDC | 2026-05-05 | Retrofitting | 62 | 52
LDC | 2026-05-12 | Retrofitting | 74 | 65
LDC | 2026-05-19 | Retrofitting | 86 | 78
LDC | 2026-05-26 | Retrofitting | 95 | 88
LDC | 2026-04-01 | Road Works | 0 | 0
LDC | 2026-04-07 | Road Works | 5 | 7
LDC | 2026-04-14 | Road Works | 14 | 16
LDC | 2026-04-21 | Road Works | 28 | 30
LDC | 2026-04-28 | Road Works | 44 | 46
LDC | 2026-05-05 | Road Works | 58 | 58
LDC | 2026-05-12 | Road Works | 70 | 66
LDC | 2026-05-19 | Road Works | 82 | 76
LDC | 2026-05-26 | Road Works | 92 | 86
LDC | 2026-04-01 | Structural Repair | 20 | 22
LDC | 2026-04-07 | Structural Repair | 34 | 38
LDC | 2026-04-14 | Structural Repair | 48 | 50
LDC | 2026-04-21 | Structural Repair | 60 | 62
LDC | 2026-04-28 | Structural Repair | 70 | 71
LDC | 2026-05-05 | Structural Repair | 80 | 80
LDC | 2026-05-12 | Structural Repair | 88 | 85
LDC | 2026-05-19 | Structural Repair | 94 | 90
LDC | 2026-05-26 | Structural Repair | 100 | 96
Site B | 2026-04-07 | Foundation | 25 | 22
Site B | 2026-04-14 | Foundation | 50 | 47
Site B | 2026-04-21 | Foundation | 75 | 73
Site B | 2026-04-28 | Foundation | 100 | 95
Site B | 2026-04-07 | Superstructure | 10 | 8
Site B | 2026-04-14 | Superstructure | 30 | 26
Site B | 2026-04-21 | Superstructure | 55 | 50
Site B | 2026-04-28 | Superstructure | 80 | 72